## Sheet1
Netflix
Environment
Month/Year (Dates) | Sandbox (test) | Staging | Production
2010-01-01 | Order DVD/CDs | Order DVD/CDs | Order DVD/CDs
2/1/2010- Business Owner of Netflix came up with a new idea that they should allow customers to stream the movies online along with ordering dvds/cds | Order DVD/CDs | Order DVD/CDs | Order DVD/CDs
2/1/2010- A BRD is created | Order DVD/CDs | Order DVD/CDs | Order DVD/CDs
4/30/2010- Requirements were finalized. In other words, FRD (Functional requirements document) was created | Order DVD/CDs | Order DVD/CDs | Order DVD/CDs
5/1/10 to 8/30/2010- Coding was impleted by the developers. | Order DVD/CDs + Stream Movies | Order DVD/CDs | Order DVD/CDs
8/20/2010 to 10/30/2010- QA will perform testing in a Sandbox environment | Order DVD/CDs + Stream Movies | Order DVD/CDs | Order DVD/CDs
Test in Staging frok 11/1/010 to 11/10/2010 | Order DVD/CDs + Stream Movies | Order DVD/CDs + Stream Movies | Order DVD/CDs
11/15/2010-- Deployment | Order DVD/CDs + Stream Movies | Order DVD/CDs + Stream Movies | Order DVD/CDs + Stream Movies